CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Ho Chi Minh, May 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 25/05/2026 | A | Hoang Nguyen Minh Hieu | Initial draft of Project Management Plan |
| 26/05/2026 | M | Vu Manh Dung | Updated RACI matrix, project deliverable due dates, and technology stack |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | User & Profile Management |  | 12 |
| 1.1 | Authentication (Login/Register) | Simple | 3 |
| 1.2 | Manage User Profile & Workspace Info | Medium | 5 |
| 1.3 | Feng Shui Element Calculation Engine | Simple | 4 |
| 2 | AI Recommendation System |  | 22 |
| 2.1 | Workspace Image Analysis via AI Vision | Complex | 10 |
| 2.2 | Feng Shui Scoring & Rule Matching | Complex | 7 |
| 2.3 | Explainable Output Generation | Medium | 5 |
| 3 | Product & 3D Integration |  | 18 |
| 3.1 | Product Management (CRUD by Garden Owner) | Medium | 6 |
| 3.2 | Integrate Image-to-3D API (Meshy.ai) | Complex | 8 |
| 3.3 | 3D Model Viewer UI integration | Medium | 4 |
| 4 | E-Commerce & Order Routing |  | 17 |
| 4.1 | Shopping Cart & Checkout Process | Medium | 7 |
| 4.2 | Order Splitting (Multiple Garden Routing) | Complex | 6 |
| 4.3 | Payment Gateway Integration (Sandbox) | Medium | 4 |
| 5 | Order Fulfillment & Support |  | 13 |
| 5.1 | Garden Staff Delivery Tracking | Simple | 5 |
| 5.2 | After-sales Support (Refund/Exchange Flow) | Medium | 8 |
| 6 | Admin Dashboard & System Config |  | 10 |
| 6.1 | Monitor System & Manage Roles | Simple | 5 |
| 6.2 | Configure AI Rules & Database | Medium | 5 |
| Total Estimated Effort (man-days) |  |  | 92 |

### 1.2 Project Objectives

The overall project objective is to deliver a fully functional web-based AI recommendation and E-commerce platform within the 14-week timeframe. The project targets high accuracy in AI feng shui matching and smooth 3D model generation, while maintaining zero critical bugs in the payment and order routing modules.

Quality

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | Documents (SRS, ERD) | < 20 | < 5% | Resolve before coding |
| 2 | Unit Test | Core Logic (AI, Order) | < 15 | < 5% | Covered by Devs |
| 3 | Integration Test | API (Meshy, Gemini) | < 10 | < 5% | Focus on API timeout |
| 4 | System Test | E2E E-commerce flow | < 10 | < 2% | UI/UX & Data Consistency |
| 5 | Acceptance Test | UAT by Mentor/Users | < 5 | < 1% | Usability & Business value |

Milestone Timeliness (%): 100% adherence to the Capstone project schedule.

Allocated Effort (man-days): 92 man-days distributed across requirements, design, coding, testing, and management.

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | AI generates incorrect Feng Shui advice. | High | Medium | Implement a Hybrid AI approach (Rule-based constraints combined with LLM generation). |
| 2 | Meshy.ai API downtime or high latency during 3D generation. | High | Medium | Implement an asynchronous polling mechanism; show user-friendly loading states. |
| 3 | E-commerce Order Routing fails when items belong to different vendors. | High | Low | Create strict ERD constraints and write comprehensive Unit Tests for the cart splitting logic. |
| 4 | Team members unfamiliar with 3D WebGL rendering libraries. | Medium | High | Allocate time in Week 1-2 for specific R&D on Three.js or model-viewer components. |

## 2. Management Approach

### 2.1 Project Process

The team will apply an Iterative Software Development Life Cycle (SDLC) mixed with Agile practices.

- We will divide the project into distinct iterations (Sprints), focusing on the "Eat the frog" approach: resolving high-risk modules (AI Recommendation & 3D Integration) in the earliest iterations.

- Later iterations will cover E-commerce functionalities, Admin tools, and system polishing.

### 2.2 Quality Management

- Defect Prevention: Strict ERD and architecture reviews before coding.

- Reviewing: Peer code reviews on GitHub before merging into the main branch.

- Unit Testing: Focus testing on the order calculation logic and rule-based feng shui engine.

- Integration Testing: Rigorous testing of third-party API communication (Gemini API, Meshy API).

- System Testing: End-to-end testing of the 5 main business flows.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Python (FastAPI) & AI Prompts | Backend/AI Dev | Week 1, 3 days | Mandatory |
| 3D Web Integration (Three.js) | Frontend Dev | Week 2, 3 days | Mandatory |
| Git, GitHub Collaboration | All Members | Week 1, 1 day | Mandatory |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 & 2 (Intro & Management Plan) | 28/05/2026 | Document |
| 2 | Report 3 (SRS & System Architecture) | 11/06/2026 | Document & UML/ERD |
| 3 | System Prototype (AI & 3D PoC) | 18/06/2026 | Source Code / Demo |
| 4 | Core E-commerce Implementation | 09/07/2026 | Source Code |
| 5 | Testing & Bug Fixing | 16/07/2026 | Test Logs |
| 6 | Final Application Deployment | 23/07/2026 | Live URL |
| 7 | Final Presentation & User Manual | 01/08/2026 | Slides & Document |

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | HieuHnmSE182738 | DungVMSE184404 | TriNCSE182049 | VuNTASE182569 |
| --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | R | I | I |
| Prepare Project Introduction Document | S | D | S | S |
| Prepare SRS Document (Overview Part) | S | D | S | S |
| Prepare SRS Document (User Requirements) | D | S | I | S |
| E-Commerce & Order Module | S | D | R | I |
| AI Recommendation Module | D | S | S | I |
| 3D Integration (Meshy.ai) | S | S | D | S |
| Testing & QA | R | S | S | D |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily Stand-up | Internal Team | Track progress, blockages | Daily | Online, Zalo/Discord |
| Weekly Sync | Internal Team | Merge code, review task | Weekly | Offline meeting |
| Mentor Feedback | Mentor & Team | Report progress, get advice | Bi-weekly | Offline / Google Meet |

## 6. Configuration Management

### 6.1 Document Management

All project documents (SRS, Reports, Presentation slides) will be centrally managed and version-controlled on Google Drive. Major milestones will be exported as PDF files.

### 6.2 Source Code Management

Source code will be hosted on GitHub. The team will use a Git Flow branching strategy (main for production, dev for integration, and feature/xxx branches for individual tasks) to prevent conflicts.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | React (FrontEnd), .Net Core (BackEnd) |
| Database | PostgreSQL |
| IDEs/Editors | Visual Studio Code, Visual Studio, Rider |
| Diagramming | StarUML, DrawIO |
| Documentation | Ms Office, Google Docs/Sheets/Slides |
| Version Control | Github (Source Codes), Google Drive (Documents) |
| Deployment server | MonsterASP (BE, Db) Vercel (FE), FireBase |
| Project management | ProjectLibre (Schedule), Github(Tasks, Defects) |