## Cover
TEST REPORT DOCUMENT
|  | SU26SE093 |  |  | 17/08/2026
Project Name | FengDesk AI - Intelligent Workspace Feng Shui Plant Recommendation & E-Commerce Platform |  |  | Creator | 1
Project Code | SU26SE093 |  |  | Issue Date | 17/08/2026
Document Code | SU26SE093_XXX_vx.x |  |  | Version
17/08/2026 | 1 | All sheets | A | Initial version of the integration test report. | Report5_Test Documentation.docx
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
17/08/2026 | 2 | Authentication, Test Statistics | A | Added the 17 multi-step authentication cases (registration, forgot password, change of email) that were executed but not yet listed. The workbook now holds all 88 integration cases. | Report5_Test Documentation.docx
Note on D10: *A: Add M: Modify D: Delete

## Test Cases
TEST CASE LIST
Project Name |  | #REF!
Project Code |  | API hosted in process over real HTTP, backed by a PostgreSQL database dedicated to testing. External services (SMTP, PayOS, GHN, Meshy, Google, LLM relay) are replaced by in-process fakes. Command: dotnet test FengDeskAI.slnx
Test Environment Setup Description |  | <List enviroment requires in this system 1. Server 2. Database 3. Web Browser ... >
1 | Authentication | Authentication | UC-01 Register / Login. Sign in, current user profile and Google sign in. Flows that need a real mailbox are out of scope (section 1.2). | See the Pre-Condition column of each case in the feature sheet.
2 | Cart and Checkout | Cart and Checkout | UC-09, UC-10. Shopping cart, checkout and the splitting of one cart into one sub order per garden (BR-04, BR-05). | See the Pre-Condition column of each case in the feature sheet.
3 | Payment and Cancellation | Payment and Cancellation | UC-11. Payment link creation for online orders and order cancellation. Real settlement is out of scope (section 1.2). | See the Pre-Condition column of each case in the feature sheet.
4 | Delivery | Delivery | UC-20, UC-23. Visibility of deliveries for the garden that must fulfil them. | See the Pre-Condition column of each case in the feature sheet.
5 | Returns Refunds and Exchanges | Returns Refunds and Exchanges | UC-15, UC-28, UC-29, UC-30. Return request, staff decision and refund. Photo evidence is mandatory (BR-08) and dead plants are never recalled (BR-09). | See the Pre-Condition column of each case in the feature sheet.
6 | API Authorization and Robustness | API Authorization and Robustnes | Cross cutting. Generated from the routing table, so all 242 endpoints are covered and any endpoint added later is covered automatically. | See the Pre-Condition column of each case in the feature sheet.

## Test Statistics
TEST STATISTICS
| FengDesk AI - Intelligent Workspace Feng Shui Plant Recommendation & E-Commerce Platform |  |  | Vu Manh Dung
Project Name | SU26SE093 |  | Creator
Project Code | SU26SE093_Test Report_v1.0 |  | Reviewer/Approver |  |  | 17/08/2026
Document Code | Authentication, cart and checkout, payment and cancellation, delivery, returns and refunds, API authorization and robustness. |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
1 | Authentication | 33 | 0 | 0 | 0 | 33
2 | Cart and Checkout | 11 | 0 | 0 | 0 | 11
3 | Payment and Cancellation | 6 | 0 | 0 | 0 | 6
4 | Delivery | 2 | 0 | 0 | 0 | 2
5 | Returns Refunds and Exchanges | 15 | 0 | 0 | 0 | 15
6 | API Authorization and Robustness | 21 | 0 | 0 | 0 | 21
| Sub total | 88 | 0 | 0 | 0 | 88

## Authentication
Authentication
Feature | UC-01 Register / Login. Registration, sign-in, account recovery, change of email, Google sign-in and the access token of every role. | [10 empty] | Passed
Test requirement | 33 | [10 empty] | Failed
Number of TCs | 33 | [10 empty] | Pending
Round 1 | 33 | 0 | 0 | 0 | [7 empty] | N/A
Round 2 | 33 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
AUTH-LOGIN-01 | [Normal] Sign in with a correct email and password | Send POST /api/Auth/login with the correct email and password of the Customer account | Returns 200 with an access token, a refresh token and the user profile | A Customer account exists and is active | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-LOGIN-02 | [Abnormal] Sign in with a wrong password | Send POST /api/Auth/login with the correct email but a wrong password | Returns 401 with a generic message that does not reveal whether the email or the password was wrong | A Customer account exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-LOGIN-03 | [Abnormal] Sign in with an email that is not registered | Send POST /api/Auth/login with an email that was never registered | Returns 401 with exactly the same message as the wrong-password case, so registered emails cannot be enumerated | The email does not exist in the system | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-LOGIN-04 | [Boundary] Sign in with an empty password | Send POST /api/Auth/login with an empty password string | Returns 401 without raising a server error | A Customer account exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-LOGIN-05 | [Normal] Sign in with the email in a different letter case | Send POST /api/Auth/login with the email written entirely in uppercase | Returns 200 because the email is normalised to lowercase before lookup | A Customer account exists with a lowercase email | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-ME-01 | [Abnormal] Call the current-user endpoint without signing in | Send GET /api/Auth/me without a bearer token | Returns 401 | No Authorization header is attached | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-ME-02 | [Normal] Call the current-user endpoint with a valid token | Send GET /api/Auth/me with the Customer bearer token | Returns 200 with the profile of the signed-in account | Signed in as the Customer account | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-GOOGLE-01 | [Normal] First Google sign in creates a new account | Send POST /api/Auth/google with a valid Google credential for an email that has no account | Returns 200 with an access token; the account is created with no password | The email has never been registered | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-GOOGLE-02 | [Abnormal] A Google only account cannot sign in with a password | Create an account through Google sign in, then call POST /api/Auth/login with that email | Returns 401 because the account has no password yet | The account was created through Google sign in | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-GOOGLE-03 | [Abnormal] An invalid Google ID token is rejected | Send POST /api/Auth/google with a made up credential | Returns 401 and no account is created | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-TOKEN-01 | [Normal] The Customer token reaches the current user endpoint | Sign in as Customer, then call GET /api/Auth/me with that token | Returns 200 with the profile of the Customer account | A Customer account exists and is active | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-TOKEN-02 | [Normal] The Staff token reaches the current user endpoint | Sign in as Staff, then call GET /api/Auth/me with that token | Returns 200 with the profile of the Staff account | A Staff account exists and is active | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-TOKEN-03 | [Normal] The Manager token reaches the current user endpoint | Sign in as Manager, then call GET /api/Auth/me with that token | Returns 200 with the profile of the Manager account | A Manager account exists and is active | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-TOKEN-04 | [Normal] The Admin token reaches the current user endpoint | Sign in as Admin, then call GET /api/Auth/me with that token | Returns 200 with the profile of the Admin account | A Admin account exists and is active | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-TOKEN-05 | [Normal] The Garden Owner token reaches the current user endpoint | Sign in as Garden Owner, then call GET /api/Auth/me with that token | Returns 200 with the profile of the Garden Owner account | A Garden Owner account exists and is active | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-TOKEN-06 | [Abnormal] The current user endpoint refuses a request without a token | Send GET /api/Auth/me with no Authorization header | Returns 401 | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-REG-01 | [Normal] Complete the three-step registration with a new email | Send POST /api/Auth/register/initiate with an unused email, read the OTP, send POST /api/Auth/register/verify, then POST /api/Auth/register/finalize with the registration token and a password | Returns 201 with an access token, and the new account signs in immediately with that password | The email has never been registered | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-REG-02 | [Abnormal] Register with an email that already has an account | Send POST /api/Auth/register/initiate with the email of an existing Customer account | Returns 409 and no OTP is issued | A Customer account exists with that email | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-REG-03 | [Abnormal] The registration token can only be used once | Complete the first two registration steps, then send POST /api/Auth/register/finalize twice with the same registration token | The first call returns 201, the second returns 401 | The email has never been registered | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-REG-04 | [Abnormal] Too many wrong OTP attempts lock the code | Request a registration OTP, then send POST /api/Auth/register/verify six times with a wrong OTP | Returns 400 with a message stating the code was tried too many times | A registration OTP has just been issued | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-01 | [Normal] Send a password-reset OTP to a registered email | Send POST /api/Auth/forgot-password/initiate with the email of the Customer account | Returns 200 and an OTP is sent to that mailbox | A Customer account exists and is active | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-02 | [Abnormal] Send a password-reset OTP to an unregistered email | Send POST /api/Auth/forgot-password/initiate with an email that was never registered | Returns 404, a deliberate decision that favours a clear user experience over resisting email enumeration | The email does not exist in the system | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-03 | [Abnormal] Request an OTP with a malformed email | Send POST /api/Auth/forgot-password/initiate with a string that is not an email | Returns 400 with an invalid-email message | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-04 | [Boundary] Request an OTP with an empty email | Send POST /api/Auth/forgot-password/initiate with an empty email string | Returns 400 without raising a server error | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-05 | [Abnormal] Verify a wrong OTP | Send POST /api/Auth/forgot-password/verify with an incorrect OTP | Returns 400 and issues no resetPasswordToken | A Customer account exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-06 | [Abnormal] Reset the password with an invalid token | Send POST /api/Auth/forgot-password/reset with a made-up resetPasswordToken | Returns 401 with an invalid-session message | No password-reset session is open | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-07 | [Boundary] Reset the password with a 5-character password, one below the minimum of 6 | Send POST /api/Auth/forgot-password/reset with a 5-character newPassword | Returns 400 stating the 6-character minimum; the check runs before the token is consumed | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-08 | [Boundary] Reset the password with an empty password | Send POST /api/Auth/forgot-password/reset with an empty newPassword | Returns 400 stating the password must not be empty | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-09 | [Normal] The full forgot-password flow revokes every existing session | Register an account and sign in to obtain a refresh token, then run the three forgot-password steps and set a new password | Returns 200; the old password no longer signs in, the new one does, and the refresh token issued before the change is refused with 401 | An account exists and has an active session | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-10 | [Abnormal] The reset-password token can only be used once | Run the forgot-password steps to obtain a resetPasswordToken, then call POST /api/Auth/forgot-password/reset twice with it | The first call returns 200, the second returns 401 | An account exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-FP-11 | [Abnormal] A new password identical to the current one is rejected | Run the forgot-password steps, then reset the password to the value the account already uses | Returns 400 with a message stating the new password repeats the current one | An account exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-EMAIL-01 | [Normal] Complete the four-step email change | Signed in, call POST /api/Auth/me/email/initiate, verify the OTP sent to the current address, request the new address, then confirm the OTP sent to it | Returns 200 at every step; the account then signs in with the new email and no longer with the old one | Signed in as an account whose current email can be read | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
AUTH-EMAIL-02 | [Abnormal] Skipping the current-email verification is blocked | Signed in, call POST /api/Auth/me/email/request-new with an invented changeEmailToken | Returns 401 and the email is not changed | Signed in as a Customer | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Cart and Checkout
Cart and Checkout
Feature | UC-09, UC-10. Shopping cart, checkout and the splitting of one cart into one sub order per garden (BR-04, BR-05). | [10 empty] | Passed
Test requirement | 11 | [10 empty] | Failed
Number of TCs | 8 | [10 empty] | Pending
Round 1 | 11 | 0 | 0 | 0 | [7 empty] | N/A
Round 2 | 11 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
SALES-CART-01 | [Normal] Add a product to the cart and read the cart back | Add two units of a product variant, then read GET /api/cart | The cart holds one line with quantity two and the subtotal equals price times two | A store with a product variant in stock exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-CART-02 | [Abnormal] Adding to the cart with quantity zero is rejected | Send POST /api/cart/items with quantity zero | Returns 400 and nothing is added | A store with a product variant exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-CART-03 | [Abnormal] Adding more units than the available stock is rejected | Send POST /api/cart/items with a quantity above the stock of the variant | Returns 400 with a message about the remaining stock | The variant has a known stock level | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-CART-04 | [Abnormal] Adding an unknown product variant returns not found | Send POST /api/cart/items with an identifier that does not exist | Returns 404 | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-ORDER-01 | [Normal] A cart spanning two stores splits into two deliveries | Add one product of store A and one of store B, then check out with cash on delivery | The order is created with two deliveries, one per store, each with its own subtotal | Two stores each with a product variant in stock, and a default shipping address | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-ORDER-02 | [Normal] A cart from a single store creates one delivery | Add one product of a single store, then check out | The order is created with exactly one delivery | One store with a product variant in stock | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-ORDER-03 | [Abnormal] Checking out an empty cart is rejected | Empty the cart, then send POST /api/orders | Returns 400 and no order is created | The cart is empty | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-ORDER-04 | [Abnormal] Checkout with an unknown shipping address is rejected | Add a product, then check out with a shipping address identifier that does not exist | Returns 400 and no order is created | The cart holds at least one line | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-ORDER-05 | [Normal] Ordered items are removed from the cart after checkout | Add a product, check out, then read GET /api/cart | The cart is empty | The cart holds exactly the products being ordered | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-ORDER-06 | [Normal] A placed order appears in the customer order history | Place an order, then read GET /api/orders and GET /api/orders/{id} | The order appears in the list and its detail can be opened | The customer has placed at least one order | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-ORDER-07 | [Abnormal] An order is not visible to another customer | Place an order as customer A, register customer B, then read the order as customer B | Returns 404 for customer B | Two separate customer accounts exist | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Payment and Cancellation
Payment and Cancellation
Feature | UC-11. Payment link creation for online orders and order cancellation. Real settlement is out of scope (section 1.2). | [10 empty] | Passed
Test requirement | 6 | [10 empty] | Failed
Number of TCs | 3 | [10 empty] | Pending
Round 1 | 6 | 0 | 0 | 0 | [7 empty] | N/A
Round 2 | 6 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
SALES-PAY-01 | [Normal] Create a payment link for an online order | Place an order with the online payment method, then send POST /api/payments/{orderId} | Returns a checkout link for the order | An order awaiting online payment exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-PAY-02 | [Abnormal] A cash on delivery order cannot create an online payment link | Place a cash on delivery order, then send POST /api/payments/{orderId} | Returns 400 with a message that a cash order is paid on delivery | A cash on delivery order exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-PAY-03 | [Abnormal] Creating a payment link for an unknown order returns not found | Send POST /api/payments/{orderId} with an identifier that does not exist | Returns 404 | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-PAY-04 | [Abnormal] The payment webhook survives a malformed payload | Send POST /api/payments/payos/webhook with a body that does not match the expected shape | Answers with a client error, never with a server error | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-CANCEL-01 | [Normal] Cancel an order while it is still pending | Place an order, then send POST /api/orders/{id}/cancel | The order moves to the cancelled state | An order in the pending state exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-CANCEL-02 | [Abnormal] Cancelling the same order twice is rejected | Cancel an order, then cancel it again | The second call is refused | An order that has already been cancelled | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Delivery
Delivery
Feature | UC-20, UC-23. Visibility of deliveries for the garden that must fulfil them. | [10 empty] | Passed
Test requirement | 2 | [10 empty] | Failed
Number of TCs | 0 | [10 empty] | Pending
Round 1 | 2 | 0 | 0 | 0 | [7 empty] | N/A
Round 2 | 2 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
SALES-DELIVERY-01 | [Normal] A store owner can list the deliveries of their own store | Place an order against the store, then read GET /api/orders/stores/{storeId}/deliveries as the owner | Returns 200 with the deliveries of that store | The store has at least one delivery | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
SALES-DELIVERY-02 | [Abnormal] A customer cannot list the deliveries of a store | Read GET /api/orders/stores/{storeId}/deliveries with a customer token | Returns 403 or 401 | A store exists | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Returns Refunds and Exchanges
Returns Refunds and Exchanges
Feature | UC-15, UC-28, UC-29, UC-30. Return request, staff decision and refund. Photo evidence is mandatory (BR-08) and dead plants are never recalled (BR-09). | [10 empty] | Passed
Test requirement | 15 | [10 empty] | Failed
Number of TCs | 12 | [10 empty] | Pending
Round 1 | 15 | 0 | 0 | 0 | [7 empty] | N/A
Round 2 | 15 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
RMA-01 | [Normal] A customer opens a return request on a delivered order | Drive an order to the delivered state, then send POST /api/returns with evidence images | The request is created in the Requested state | An order whose delivery reached the delivered state | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-02 | [Abnormal] A return request without evidence images is rejected | Send POST /api/returns with an empty list of image URLs | Returns 400 with a message that evidence is required | An order whose delivery reached the delivered state | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-03 | [Abnormal] A return request on a delivery that was never delivered is rejected | Place an order and, without advancing the delivery, send POST /api/returns | Returns 400 | An order whose delivery is still pending | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-04 | [Abnormal] Returning more units than were delivered is rejected | Send POST /api/returns with a quantity above the delivered quantity | Returns 400 | A delivered order of a known quantity | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-05 | [Boundary] Returning zero units is rejected | Send POST /api/returns with quantity zero | Returns 400 | A delivered order | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-06 | [Normal] A customer cancels their own request while it is still pending | Open a request, then send POST /api/returns/{id}/cancel | The request moves to the cancelled state | A request in the Requested state | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-07 | [Abnormal] Cancelling the same request twice is rejected | Cancel a request, then cancel it again | The second call is refused with 400 or 409 | A request that has already been cancelled | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-08 | [Normal] Platform staff accepts the request for review | Send POST /api/returns/{id}/accept with a staff token | The request leaves the Requested state | A request in the Requested state | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-09 | [Normal] Platform staff rejects the request with a reason | Accept the request, then send POST /api/returns/{id}/reject with a reason | The request moves to the rejected state | A request that staff has accepted | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-10 | [Abnormal] Rejecting without a reason is refused | Send POST /api/returns/{id}/reject with an empty reason | Returns 400 | A request that staff has accepted | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-11 | [Normal] A dead plant refund reaches the refunding stage without recalling the goods | Accept a PlantHealth request, then send POST /api/returns/{id}/approve-refund | The request reaches Refunding or Completed and never passes through the physical return states | A PlantHealth request that staff has accepted | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-12 | [Abnormal] A customer cannot accept their own return request | Send POST /api/returns/{id}/accept with the customer token | Returns 403 | A request opened by that customer | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-13 | [Abnormal] A store owner cannot decide the outcome of a return request | Send POST /api/returns/{id}/approve-refund with the garden owner token | Returns 403 | A request against that store | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-14 | [Normal] The customer can see their own request in the list | Read GET /api/returns/mine | The request appears in the list | A request opened by that customer | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
RMA-15 | [Normal] Platform staff can list the pending return requests | Read GET /api/returns/pending with a staff token | Returns 200 with the queue of pending requests | At least one request is waiting | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## API Authorization and Robustnes
API Authorization and Robustness
Feature | Cross cutting. Generated from the routing table, so all 242 endpoints are covered and any endpoint added later is covered automatically. | [10 empty] | Passed
Test requirement | 21 | [10 empty] | Failed
Number of TCs | 18 | [10 empty] | Pending
Round 1 | 21 | 0 | 0 | 0 | [7 empty] | N/A
Round 2 | 21 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
API-AUTHZ-01 | [Normal] The routing table is discovered and is not empty | Read the action descriptors of the running application | 242 endpoints are discovered | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-AUTHZ-02 | [Normal] Every protected endpoint refuses a request without a token, normal data | Call all 210 protected endpoints with no Authorization header, using well formed route values | Every one answers 401 | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-AUTHZ-03 | [Boundary] Every protected endpoint refuses a request without a token, boundary data | Repeat the sweep with boundary route values such as an all zero identifier | Every one still answers 401, so authorization does not depend on the payload | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-AUTHZ-04 | [Normal] Every policy protected endpoint refuses a disallowed role, normal data | Call all 66 policy protected endpoints with a role the policy does not allow | Every one answers 403 | A token exists for each of the five roles | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-AUTHZ-05 | [Boundary] Every policy protected endpoint refuses a disallowed role, boundary data | Repeat the sweep with boundary route values | Every one still answers 403 | A token exists for each of the five roles | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-AUTHZ-06 | [Normal] No public endpoint is refused, normal data | Call all 26 public endpoints with no token | None answers 401 or 403 | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-AUTHZ-07 | [Boundary] No public endpoint is refused, boundary data | Repeat the sweep with boundary route values | None answers 401 or 403 | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-SMOKE-01 | [Normal] No parameterless read endpoint answers with a server error | Call all 47 GET endpoints that take no route parameter with an administrator token | None answers with a 5xx status | The database has been migrated and seeded | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-SMOKE-02 | [Normal] The API documentation is generated | Read the OpenAPI document of the application | The document is produced, so no route is duplicated | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-ROBUST-01 | [Normal] Normal data never causes a server error | Call all 242 endpoints with well formed data | No endpoint answers with a 5xx status | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-ROBUST-02 | [Boundary] Boundary data never causes a server error | Call all 242 endpoints with boundary values such as an all zero identifier and empty fields | No endpoint answers with a 5xx status | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
API-ROBUST-03 | [Abnormal] Malformed data never causes a server error | Call all 242 endpoints with invalid identifiers, invalid JSON, negative quantities and SQL syntax | Every endpoint answers with a client error, none with a 5xx status | The application is running | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-01 | [Normal] A connection string pointing at localhost is accepted | Start the suite with Host=localhost | The suite runs | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-02 | [Normal] A connection string pointing at 127.0.0.1 is accepted | Start the suite with Host=127.0.0.1 | The suite runs | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-03 | [Normal] A connection string using the container host name is accepted | Start the suite with Server=postgres, as used on the CI runner | The suite runs | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-04 | [Abnormal] A production database connection is refused | Start the suite with a connection string pointing at the Supabase production host | The suite stops before touching the database | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-05 | [Abnormal] Any other remote host is refused | Start the suite with a connection string pointing at an arbitrary remote host | The suite stops before touching the database | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-06 | [Abnormal] A missing connection string stops the suite with guidance | Start the suite with the setting absent | The suite stops and prints the two supported ways to configure it | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-07 | [Boundary] An empty connection string is refused | Start the suite with an empty setting | The suite stops with the same guidance | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-08 | [Boundary] A whitespace only connection string is refused | Start the suite with a setting containing only spaces | The suite stops with the same guidance | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
ENV-GUARD-09 | [Abnormal] A connection string with no host segment is refused | Start the suite with a connection string that declares no host | The suite stops before touching the database | None | Passed | 17/08/2026 | Vu Manh Dung | Passed | 17/08/2026 | Vu Manh Dung | Automated
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case